## Sheet1
Day | Task
Day 1 (Jun 3) | Introduction to power electronics, begin software setup (LT Spice, Altium)
Day 2 (Jun 4) | Complete software setup, start studying voltage pulse generators
Day 3 (Jun 5) | MOSFET characteristics study
Day 4 (Jun 6) | Power electronics converters - circuit practice (Examples 1-6)
Day 5 (Jun 7) | Power electronics converters - circuit practice (Examples 7-12)
Weekend Off (Jun 8-9) | Weekend Off
Day 6 (Jun 10) | Buck converter design, calculations, and LT Spice simulation
Day 7 (Jun 11) | Boost converter design, calculations, and LT Spice simulation
Day 8 (Jun 12) | Buck-Boost converter design, calculations, and LT Spice simulation
Day 9 (Jun 13) | Forward converter (CCM & DCM) design and LT Spice simulation
Day 10 (Jun 14) | Flyback converter design and LT Spice simulation
Weekend Off (Jun 15-16) | Weekend Off
Day 11 (Jun 17) | Pushpull converter design and LT Spice simulation
Day 12 (Jun 18) | Review and compare different converter topologies
Day 13 (Jun 19) | Study NCP51820 Gate Driver specifications and applications
Day 14 (Jun 20) | GaN 3R2_100 CBE MOSFET and Nexperia MOSFET study
Day 15 (Jun 21) | Symbol and component creation in LT Spice and Altium PCB design
Weekend Off (Jun 22-23) | Weekend Off
Day 16 (Jun 24) | Introduction to PCB layout principles in Altium
Day 17 (Jun 25) | Altium PCB design practice - schematic creation
Day 18 (Jun 26) | Altium PCB design practice - component placement and routing basics
Day 19 (Jun 27) | Altium PCB design practice - advanced routing techniques
Day 20 (Jun 28) | Altium PCB design practice - design rule checks and optimization
Weekend Off (Jun 29-30) | Weekend Off
Day 21 (Jul 1) | Synchronous Buck-Boost converter design principles
Day 22 (Jul 2) | Synchronous Buck-Boost converter simulation in LT Spice
Day 23 (Jul 3) | Evaluation board design - study ON Semiconductor datasheets
Day 24 (Jul 4) | Evaluation board schematic design based on ON Semi reference
Day 25 (Jul 5) | Evaluation board PCB layout in Altium - Part 1
Weekend Off (Jul 6-7) | Weekend Off
Day 26 (Jul 8) | Evaluation board PCB layout in Altium - Part 2
Day 27 (Jul 9) | Evaluation board design refinement and design rule checks
Day 28 (Jul 10) | Finalize evaluation board design
Day 29 (Jul 11) | Prepare documentation for evaluation board
Day 30 (Jul 12) | Review and consolidate all internship learnings
Weekend Off (Jul 13-14) | Weekend Off
Day 31 (Jul 15) | Final project presentation preparation
Day 32 (Jul 16) | Final project presentation and internship wrap-up

## Sheet2
From 3-06-2024 to 16-07-2024
S. No | Field | Power Electronics
1 | Project Title | Power Electronic Circuits - Numerical Simulations
2 | Project Description | This project aims to design and simulate various power electronic circuits, such as converters using numerical simulation techniques.
3 | Outline of the Solution | Identify the power electronic circuits to be designed and simulated. Develop mathematical models for the selected circuits. Implement numerical simulation algorithms to analyze the circuit behavior. Validate the simulation results against theoretical calculations or experimental data.
4 | Design of the Solution | Formulate the mathematical equations governing the circuit behavior. Choose appropriate numerical simulation methods based on the circuit complexity and desired accuracy. Develop simulations to solve the numerical equations and simulate the circuit performance. Optimize the simulation parameters for efficient and accurate results.
5 | Hardware and Software Requirements to execute the project | LT spice, Altium PCB Design and Spread sheet
6 | Environment setup windows/linux/Raspberry pi/Arduino | Windows
7 | Concepts Used (Functions, header files, data types, and concepts (Loops, arrays, conditional statements, etc.). Explanation of the concepts). For Hardware projects also explain with respect to the code being developed | Design of Specific required GaN based MOSFET and Gate drivers from the manufacture datasheet
8 | Testing & Validation (Boundary tests and boundaries of inputs. Possible inputs and corresponding outputs). | Compare simulation results with theoretical calculations or experimental data to validate the accuracy of the numerical models.
9 | Testing Material (Screenshots of working outputs. Images in case of hardware project | All validated and simulated data mentioned in detail in documentation
10 | User Manual | Run the simulations and interpret the results. Guidelines for modifying the circuit parameters and simulation settings.
11 | Technical Documentation | Detailed explanation of the mathematical models and numerical simulation algorithms used. Analysis of the simulation results and their implications for power electronic circuit design.
12 | References | Related Reference documents are mentioned in documentation
Daily Work Breakdown
Week 1 From 3/06/2024 - 07/06/2024
| Day 1 | Introduction to power electronics, begin software setup (LT Spice, Altium)
| Day 2 | Complete software setup, start studying voltage pulse generators
| Day 3 | MOSFET characteristics study
| Day 4 | Power electronics converters - circuit practice (Examples 1-6)
| Day 5 | Power electronics converters - circuit practice (Examples 7-12)
Week 2 From 10/06/2024 - 04/06/2024
| Day 1 | Buck converter design, calculations, and LT Spice simulation
| Day 2 | Boost converter design, calculations, and LT Spice simulation
| Day 3 | Buck-Boost converter design, calculations, and LT Spice simulation
| Day 4 | Forward converter (CCM & DCM) design and LT Spice simulation
| Day 5 | Flyback converter design and LT Spice simulation
Week 3 From 17/06/2024 - 21/06/2024
| Day 1 | Pushpull converter design and LT Spice simulation
| Day 2 | Review and compare different converter topologies
| Day 3 | Study NCP51820 Gate Driver specifications and applications
| Day 4 | GaN 3R2_100 CBE MOSFET and Nexperia MOSFET study
| Day 5 | Symbol and component creation in LT Spice and Altium PCB design
Week 4 From 24/06/2024 - 28/06/2024
| Day 1 | Introduction to PCB layout principles in Altium
| Day 2 | Altium PCB design practice - schematic creation
| Day 3 | Altium PCB design practice - component placement and routing basics
| Day 4 | Altium PCB design practice - advanced routing techniques
| Day 5 | Altium PCB design practice - design rule checks and optimization
Week 5 From 01/07/2024 - 05/07/2024
| Day 1 | Synchronous Buck-Boost converter design principles
| Day 2 | Synchronous Buck-Boost converter simulation in LT Spice
| Day 3 | Evaluation board design - study ON Semiconductor datasheets
| Day 4 | Evaluation board schematic design based on ON Semi reference
| Day 5 | Evaluation board PCB layout in Altium - Part 1
Week 6 From 08/07/2024 - 12/07/2024
| Day 1 | Evaluation board PCB layout in Altium - Part 2
| Day 2 | Evaluation board design refinement and design rule checks
| Day 3 | Finalize evaluation board design
| Day 4 | Prepare documentation for evaluation board
| Day 5 | Review and consolidate all internship learnings
Week 7 From 15/07/2024 - 16/07/2024
| Day 1 | Final project presentation preparation
| Day 2 | Final project presentation and internship wrap-up